TRAINING/PROJECT PROPOSAL

- Empowering Small-Scale Vegetable Growers for Sustainable Production and Management in Zamboanga del Sur: Phase 2

II. PROPONENTS

- Project Leader – Jean Rose C. Vanguardia

- Ass. Leader – Maria Leah S. Chiong

- Members –  Gypsie Claudine F. Café

- Lanelyn B.  Nillas

SDG Alignment :

- SDG 2 – Zero Hunger

- SDG 8 – Decent Work and Economic Growth

- SDG 12 – Responsible Consumption and Production

- SDG 17 – Partnerships for the Goals

TABANGE Framework Alignment:

- Barangay Empowerment and Good governance

III. PROJECT DURATION- January to December 2027

IV. PROJECT COST- Php 60,000.00

V. PARTNER AGENCIES: Barangay Local Government of Lapuyan

VI. LOCATION / SITE: Lapuyan, Zamboanga del Sur

VII. PARTICIPANTS/BENEFICIARIES: 50 Vegetable Farmers in Lapuyan, ZDS (members of the Local Association)

VIII. RATIONALE/BACKGROUND

Pesticide misuse is a prevalent issue in many vegetable-growing communities in the Philippines, resulting in environmental degradation, health risks, and the development of pest resistance. In Claveria, Misamis Oriental, a recent study (Gonzaga et al., 2020) found that a significant proportion of farmers have not received formal training in pest management, resulting in an overreliance on chemical pesticides.

These challenges are not unique to Claveria; similar crop types, pest pressures, and pesticide usage patterns exist in other vegetable-producing regions, including Zamboanga del Sur. This creates an opportunity to scale and adapt proven recommendations from the Claveria study to a new context, ensuring relevance to local conditions.

IX. GENERAL AND SPECIFIC OBJECTIVES

This project aims to enhance the sustainable vegetable production and management practices of small-scale growers in Lapuyan, Zamboanga del Sur, through capacity-building interventions, improved farming systems, and the establishment of farmer-led support mechanisms.

Specific Objectives:

- Improve farmers’ decision-making skills through demonstrations and hands-on activities.

- To retrain and enhance the knowledge and skills of small-scale vegetable growers in Lapuyan ZDS on improved vegetable production techniques, sustainable farming practices, and proper farm management.

- To improve the productivity and income of small-scale vegetable growers by promoting proper farm management, efficient use of farmer-provided inputs, and improved production and marketing practices.

- To strengthen the capacity and sustainability of small-scale vegetable growers through organized collaboration, continuous technical support, and linkages with relevant government agencies, institutions, and markets.

X. METHODOLOGY

| SESSION / TOPIC | TIMEFRAME | ENABLER | EXPECTED OUTPUT |
| --- | --- | --- | --- |
| - Training and Reorientation on Improved Vegetable Production Techniques | January 2027 | Project Team / Implementers | Training Report, Needs Assessment Results, Attendance |
| - Hands-on Demonstration on Efficient Use of Inputs, and Farm Management | February 2027 | Project Team / Implementers | Demonstration Report, Farmer Outputs, Attendance |
| - Sustainable Vegetable Production and Proper Farm Management assessment | February–March 2027 | Project Team | Attendance, Training Outputs, Farmer Action Plans |
| - Evaluation on Vegetable Production, Marketing, and Income Improvement of farmers | March 2027 | Project Team / Implementers | Attendance, Marketing Plan, Production and Income Records |
| - Farmer Linkages and continuous Collaboration | March–April 2027 | Project Team / Implementers / Partner Agencies | FLSG Records, Linkage Records, Attendance, Follow-up Reports |

XI. HIGHLIGHT OF THE PROJECT

### A. Project Involvement

Faculty implementers, MAO – LGU representatives, and farmer leaders.

### B. Beneficiaries

50 vegetable farmers from the local association.

### C. Project Components

Management & Coordination

Series of retraining’s, redemonstrations, monitoring and evaluation

Support Network Formation (Farmer Lead Network Support)

XIII. SUSTAINABILITY PLAN

| Strategy | Description | Responsible Group |
| --- | --- | --- |
| Farmer-Led Support Network | Establish regular peer mentoring, meetings, and communication/chat groups where trained farmers can share experiences, provide technical advice, and support other small-scale vegetable growers in applying improved and sustainable production practices. | Farmer Leaders / Farmer Associations |
| Integration with LGU Programs | Coordinate with the Municipal Agriculture Office (MAO) and Barangay Local Government Units (BLGUs) to continue technical assistance, monitoring, and inclusion of vegetable growers in relevant agricultural programs and services. | Municipal Agriculture Office / Barangay Local Government Unit, Lapuyan, ZDS |
| Resource Sharing | Promote collective management and sharing leaflets materials and technical knowledge to the farmers and MAO LGU will provide assistance on inputs, etc. | MAO-LGU / Farmer Associations |
| Continuous Technical Support | Conduct periodic farm visits, follow-up activities, and technical consultations to help farmers sustain improved vegetable production, proper farm management, and sustainable farming practices. | Project Team / MAO-LGU / Farmer Leaders |
| Production and Marketing Linkages | Strengthen coordination among farmer associations, local institutions, and potential organizations to support improved production planning, collective marketing, and better income opportunities for vegetable growers. | Farmer Associations / MAO-LGU / Relevant Organizations |
| Farmer Monitoring and Record-Keeping | Encourage farmers to maintain simple records of production, input use, farm expenses, yields, and sales to improve decision-making and monitor changes in productivity and income. | Project Team / MAO-LGU |
| Sustainability and Capacity Building | Provide continued mentoring for the farmer leaders and facilitating activities after the project period, and transfer technology to the partner MAO-LGU after termination. | Project Team / MAO-LGU |

XIV. BUDGETARY REQUIREMENTS

The budgetary requirements shall cover the expenses necessary for the conduct of farmer trainings, demonstrations, hands-on activities, training materials, farm inputs, monitoring and evaluation, and other project implementation activities.

| ITEM DESCRIPTION |  | UNIT OF ISSUE | QUANTITY | UNIT PRICE |  | TOTAL COST |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| I. OFFICE SUPPLIES |  |  |  |  |  |  |  |
| Notebook (30 leaves) |  | piece | 50 | 15.00 |  | 750.00 |  |  |  |
| Ball Pen (Black, 0.5mm) |  | Box (50 pieces) | 1 | 450.00 |  | 450.00 |  |  |  |
| Bond paper (Legal) |  | ream | 1 | 280.00 |  | 280.00 |  |  |  |
| Subtotal |  |  |  |  |  | 1480.00 |  |  |  |
| II. PRINTING EXPENSE |  |  |  |  |  |  |  |
| Tarpaulin (4x6 feet) |  | pcs | 1 | 600.00 |  | 600.00 |  |  |  |
| Subtotal |  |  |  |  |  | ₱600.00 |  |  |  |
| III.REPRESENTATION (MEALS) |  |  |  |  |  |  |  |
| January 2027 | AM Snack: Siopao & C2 | pax | 55 |  | 150.00 |  | 8,250.00 |  |
| February, 2027 | AM Snack: Banana cake & C2 | pax | 55 |  | 150.00 |  | 8,250.00 |  |
| March 2027 | AM Snack: Torta & Lemon Juice | pax | 55 |  | 150.00 |  | 8,250.00 |  |
| April 2027 | AM Snack: Cinnamon bread & C2 | pax | 55 |  | 150.00 |  | 8,250.00 |  |
| May 2027 | AM Snack: Banana cake & Lemon Juice | pax | 55 |  | 150.00 |  | 8,250.00 |  |
| June 2027 | AM Snack: Cinnamon Bread & Juice in Pouch | pax | 55 |  | 150.00 |  | 8,250.00 |  |
| July 2027 | AM Snack: Siopao & Lemon Juice | pax | 55 |  | 150.00 |  | 8,250.00 |  |
| Subtotal ₱57, 750.00 |  |  |  |  |  |  |  |  |
| Grand Total ₱ 59,830.00 |  |  |  |  |  |  |  |  |

# XV. EXPECTED OUTCOMES

At the end of the project, the following five key outcomes are expected:

- Improved Knowledge and Skills – At least 50 vegetable farmers will gain improved knowledge and skills in sustainable vegetable production, farm management, and pest management.

- Adoption of Sustainable Practices – Farmers will apply improved crop management, integrated pest management (IPM), proper sanitation, and responsible use of farm inputs.

- Improved Productivity and Income – Farmers will apply efficient production and marketing practices that can improve productivity, reduce unnecessary costs, and increase profitability.

- Strengthened Farmer Support Network – A functional Farmer-Led Support Network will promote peer mentoring, knowledge sharing, and continuous technical support.

- Strengthened Institutional Linkages – Collaboration with the MAO, BLGU, and other relevant institutions will provide continuing technical assistance, agricultural services, and market opportunities.

XVI. DETAILED WORKPLAN

| Activity/Intervention | Specific Activities | Timeframe | Responsible Group | Expected Output | Means of Verification |
| --- | --- | --- | --- | --- | --- |
| 1.Training and Reorientation on Improved Vegetable Production Techniques | Conduct training on improved vegetable production, crop management, pest management, harvesting, and postharvest practices. | January 2027 | Project Team / Implementers | Farmers trained and production needs identified | Training report, needs assessment, attendance, pre/post-test |
| 2. Hands-on Demonstration on Efficient Use of Inputs and Farm Management | Demonstrate proper use of fertilizers, pesticides, seeds, water, and other farm inputs, including safe pesticide use and IPM. | February-March 2027 | Project Team / Implementers | Farmers demonstrate proper input use and farm management | Demonstration report, farmer outputs, attendance, photos |
| 3. Sustainable Vegetable Production and Proper Farm Management Assessment | Assess farmers’ application of sustainable practices and provide technical recommendations and action plans. | March-April 2027 | Project Team | Improved practices documented; farmer action plans prepared | Assessment forms, training outputs, action plans, monitoring reports |
| 4. Evaluation of Vegetable Production, Marketing, and Income Improvement | Assess production, marketing practices, farm expenses, yields, and income; introduce simple production and income record-keeping. | May-June 2027 | Project Team / Implementers | Production and marketing records and plans developed | Attendance, production/income records, marketing plans |
| 5. Farmer Linkages and Continuous Collaboration | Strengthen the Farmer-Led Support Network and link farmers with MAO, BLGU, and other relevant agencies for continuing technical and production support. | June-July 2027 and continuing follow-up | Project Team / Implementers / Partner Agencies | Functional farmer support network and institutional linkages established | FLSG records, linkage records, attendance, follow-up reports |

XVII. LOGICAL FRAMEWORK

| Narrative Summary | Objectively Verifiable Indicators | Means of Verification | Assumptions |
| --- | --- | --- | --- |
| Outputs: |  |  |  |
| - Farmers’ production needs assessed. | - Needs of 50 farmers identified. | - Needs assessment forms/results | Farmers provide accurate information. |
| - Training on improved vegetable production conducted. | - Training conducted. - 50 farmers trained. | - Training report - Attendance - Post evaluation report | Resource persons and training materials are available. |
| - Hands-on demonstration conducted. | - At least 1 hands-on demonstration conducted. - Proper input use and farm management demonstrated. | - Demonstration report - Farmer outputs - Photos | Weather and farm conditions are favorable. |
| - Sustainable production and farm-management practices assessed. | - Farmers’ practices assessed. - Technical recommendations and action plans provided. | - Assessment forms - Monitoring reports - Action plans | Farmers are willing to apply recommendations. |
| - Production, marketing, and income practices evaluated. | - Production, marketing, expenses, yield, and income assessed. - Simple record-keeping introduced. | - Production/income records - Evaluation report | Farmers are willing to keep basic farm records. |
| - Farmer support and institutional linkages strengthened. | - Farmer support network strengthened. - Linkages with MAO, BLGU, and relevant agencies facilitated. | - FLSG records - Attendance - Linkage/follow-up reports | Farmers and partner agencies remain willing to collaborate. |

XVIII. RECOMMENDATION STATEMENT FOR FUNDING

We respectfully recommend the approval and funding of this project to support small-scale vegetable growers in adopting sustainable production and management practices.

Prepared by:						Reviewed by:

JEAN ROSE C. VANGUARDIA 		               EMELYN D. TORMES, Ph.D

Project Leader 					                   Dean

Recommending Approval:

JOEL M. SABELLANO, JR., DVM		                MARK E. PATALINGHOG, Ph.D

Extension Director						     OVPRIDE

Approved:

EDGARDO H. ROSALES, Ed.D.

President